## Proposal
Start Date | End Date | Task | Critical tasks | Start on day | Task duration in days
2019-02-12 | 2019-02-14 | Group formation and decide use case | Group formation and decide use case | 0 | 2
2019-02-14 | 2019-02-15 | Decide division of labour and team roles | Decide division of labour and team roles | 2 | 1
2019-02-15 | 2019-02-19 | Write project proposal | Write project proposal | 3 | 4
2019-02-18 | 2019-02-19 | Revise project proposal | Revise project proposal | 6 | 1
2019-02-20 | 2019-02-21 | Submit project proposal | Submit project proposal | 8 | 1
2019-02-22 | 2019-02-25 | Set up GitHub account for project | Set up GitHub account for project | 10 | 3

## Project
Start Date | End Date | Task | Critical tasks | Start on day | Task duration in days
2019-02-28 | 2019-03-07 | Identify all datasets | Identify all datasets | 0 | 7
2019-03-08 | 2019-03-12 | Make datasets available in GitHub | Make datasets available in GitHub | 8 | 4
2019-03-13 | 2019-03-14 | First group work | First group work | 13 | 1
2019-03-14 | 2019-03-24 | ETL, Staging, Cleansing | ETL, Staging, Cleansing | 14 | 10
2019-03-24 | 2019-03-29 | Build Data Mart | Build Data Mart | 24 | 5
2019-03-29 | 2019-04-04 | Answer business questions | Answer business questions | 29 | 6
2019-04-04 | 2019-04-12 | Prepare all visualisations | Prepare all visualisations | 35 | 8
2019-04-12 | 2019-04-18 | Build the presentation | Build the presentation | 43 | 6
2019-04-18 | 2019-04-19 | Submit the presentation | Submit the presentation | 49 | 1
2019-04-24 | 2019-04-25 | Group Presentation & Individual assessment | Group Presentation & Individual assessment | 55 | 1